**Name of KVK:Dindori**

**Monthly Progress Report for the Month of: September-2013**

**Desp No-483**

**Date:-03-10-2013**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | **Activity and Sub-activities** | **Target** | **Achievements** | **Beneficiaries** | | **Total** |
| **No./Area** | **No./Area** |
| **(Ha)** | **(Ha)** | **SC/ST** | **Other** |
| A | Farm Advisory | | | | | |
| 1 | Demonstration (1a+1b+1c) | 16 | 16 | 110 | 10 | 120 |
| 1a | Oilseed (ha) | 05 | 05 | 13 | 0 | 13 |
| 1b | Pulses (ha) | 05 | 05 | 13 | 0 | 13 |
| 1c | Others (ha) | 11 | 11 | 97 | 10 | 107 |
| 2 | Field Days (No.) | 0 | 0 | 0 | 0 | 0 |
| 3 | Kisan Mela ,Krishak Sangoshti & Exhibition | 0 | 0 | 0 | 0 | 0 |
| 4 | Diagnostic services | 00 | 02 | 30 | 10 | 40 |
| 5 | Scientist visit to Farmers field | 10 | 20 | 1000 | 200 | 1200 |
| 6 | Farmer visit to KVK farm | 0 | 150 | 120 | 30 | 150 |
| 7 | Training for farmers (No.) Total (7a+7b) | 03 | 03 | 20 | 55 | 75 |
| 7a | Male (No.) | 02 | 02 | 15 | 51 | 66 |
| 7b | Female (No.) | 01 | 01 | 05 | 04 | 09 |
| 8 | School Dropouts (No.) Total (8a+8b) | 01 | 01 | 17 | 05 | 22 |
| 8a | Male (No.) | 01 | 01 | 17 | 05 | 22 |
| 8b | Female (No.) | 0 | 0 | 0 | 0 | 0 |
| 9 | In-Service Training (no) | 0 | 0 | 0 | 0 | 0 |
| 10 | On farm Testing **#** (No) | 04 | 04 | 20 | 08 | 28 |
| 11 | Other Extension Activities  Parthenium Eradication Camp | 01 | 01 | 19 | 06 | 25 |
|  | 5000 Farmers Survey | 5000 | 5000 | 3200 | 1800 | 5000 |

**Note: # in the column of target and achievements, no. of technologies to be mention while in case of beneficiaries, no of trials need to be mentioned.**

**Programme Coordinator**

**KVK,Dindori**